**General Education Project: Timeline**

|  |  |
| --- | --- |
| **Dates** | **Activity** |
| 7/31/2012 | Cross-Sector Meeting with Representative Proctor/ Organizational Meeting |
| 8/15/2012 | First Steering Committee Meeting, Conference Call |
| 9/21/2012 | Steering Committee Meeting, Valencia College |
| October 2012 | Chancellors Approve Faculty Committees |
| October 2012 | Approved Faculty Committee Members Informed of Appointment |
| October – December 2012 | Meetings, Faculty Discipline Committees  |
| 10/24/2012 | Articulation Coordinating Committee Update |
| December 2012 | Faculty Discipline Committee Initial Recommendations, Courses and Competencies |
| December 2012 – January 2013 | Steering Committee Meeting Review Draft Recommendations |
| January 2013 | Steering Committee Finalize Draft Recommendations |
| January 2013-May 2013 | Faculty Review/Institution (CAVP/CIA) Review\* |
| February 2013  | State Board of Education and Board of Governors Initiate Rule/Regulation Development |
| February 2013 | Recommendations Released for Public Comment\*\* |
| February 2013 | Articulation Coordinating Committee Review Draft Recommendations |
| March 2013-May 2013 | Faculty/(CAVP/CIA)/Public Comment Reviewed |
| May 2013-June 2013 | Steering Committee Finalize Recommendations |
| June 2013 | Final Recommendations Submitted to Chancellors |
| June 2013-July 2013 | State Board of Education and Board of Governors Rule/Regulation Approval |
| July 2013 | Communications to Florida College System and State University System Institutions, Courses and Competencies |

\*CAVP/CIA/Institution Review: The faculty on the campus will submit comments to Provost/Chief Academic Officer (or designee)

\*\*DOE/BOG will manage wider public comment in separate process